## Slide 1: Project Analysis and Evaluation
Project Analysis and Evaluation is a systematic process of assessing whether a proposed project is feasible, viable, and aligned with organizational objectives before committing significant resources.
Project analysis and evaluation are not named as a single process, but they are embedded across multiple knowledge areas and process groups, mainly during Initiating, Planning, Monitoring & Controlling, and Closing.
They focus on:
  Analyzing whether a project is viable, aligned with business goals, and feasible
  Evaluating project performance, progress, and outcomes against baselines and objectives

## Slide 2: Project Analysis - Business Case Analysis
Business Case Analysis (Initiating Process Group)
Purpose: To justify the project from a business perspective.
Key Questions:
  Why is this project needed?
  What value will it deliver?
  Do benefits outweigh costs?
Includes:
  Cost–benefit analysis
  Market demand
  Strategic alignment
  Risk vs reward
Example:
A bank wants to develop a mobile banking app.
  Estimated cost: ₹2 crore
  Expected benefit: ₹6 crore in 3 years
  Strategic goal: Increase digital customers
  👉 Since benefits exceed costs and align with strategy, the project is approved.

## Slide 3: Project Analysis - Feasibility Analysis
Evaluates whether the project is practically achievable.
Types of Feasibility:
  Technical feasibility
  Financial feasibility
  Operational feasibility
  Legal feasibility
  Schedule feasibility
Example: A hospital plans to implement an AI-based diagnostic system.
  Technical: Do we have AI expertise? ✔
  Financial: Budget available? ✔
  Legal: Complies with medical laws? ✔
  Schedule: Can it be done in 12 months? ❌
  👉 Schedule risk identified and addressed before approval.

## Slide 4: Project Analysis - Stakeholder Analysis
Identifies stakeholders and analyzes:
  Power
  Interest
  Influence
  Expectations
Tools:
  Power–Interest Grid
  Stakeholder Register
Example: For a highway construction project:
  Government: High power, high interest
  Local residents: Low power, high interest
  Contractors: High power, medium interest
  👉 Communication strategies are planned accordingly.

## Slide 5: Example – Power-Interest Grid
Software Project Scenario (Assumption)
Project Title: Online Learning Management System (LMS) Development Organization: ABC Technologies Project Objective: Develop and deploy a web-based LMS for a university within 8 months.
Power–Interest Grid
The Power–Interest Grid classifies stakeholders based on:
  Power: Ability to influence project decisions
  Interest: Level of concern or involvement in project outcomes
PMBOK defines four quadrants:
  Manage Closely
  Keep Satisfied
  Keep Informed
  Monitor

## Slide 6: Example

## Slide 7: Example – Stakeholder register
Identifies all project stakeholders and captures relevant information regarding their interests, influence, involvement, and impact on the project.
The stakeholder register is needed to:
Identify all stakeholders early
  Prevents missing critical stakeholders
Understand stakeholder expectations
  Helps avoid conflicts and misunderstandings
Assess influence and impact
  Enables prioritization of stakeholders
Plan communication and engagement
  Supports development of the Stakeholder Engagement Plan
Support decision-making
  Helps the project manager manage approvals, resistance, and support
Reduce project risks
  Unmanaged stakeholders are a major cause of project failure

## Slide 8: Example – Stakeholder Register
Components of a Stakeholder Register
Stakeholder Identification Information
Stakeholder Assessment Information
Stakeholder Assessment Information
  Power (High / Medium / Low)
  Interest (High / Medium / Low)
  Influence
  Impact on project success
  Attitude (Supportive, Neutral, Resistant)
Stakeholder Classification
  Internal / External
  Supporter / Neutral / Opponent
  Power–Interest category
  Engagement strategy

## Slide 9: Project Analysis - Risk Analysis
Identifies and analyzes uncertainties that may affect project objectives.
Types:
  Qualitative Risk Analysis (probability & impact)
  Quantitative Risk Analysis (numerical impact)
Example: In a software project:
  Risk: Key developer may resign
  Probability: Medium
  Impact: High
  👉 Mitigation: Cross-training team members.

## Slide 11: Risk Management
Risk is an uncertain event or condition that, if it occurs, has a positive or negative effect on one or more project objectives such as scope, schedule, cost, quality, or performance.
Key points:
  Risk is about uncertainty
  It may have negative effects (threats) or positive effects (opportunities)
  Risks exist in all projects, especially IT projects
Characteristics of Risk
  Future-oriented
  Uncertain in nature
  Has a cause and an effect
  Can impact cost, time, quality, scope, or reputation
  Can be managed but not completely eliminated

## Slide 13: Risk Managment
Types of Risk
Based on Impact
Negative Risk (Threat)
  Events that can harm the project.
  Example (IT Company):
  Cybersecurity breach delaying software release
  Key developer resigns during critical phase
Positive Risk (Opportunity)
  Events that can benefit the project.
  Example:
  Use of a new automation tool reduces development time
  Client requests additional features with extra payment

## Slide 14: Types of Risk in IT Projects
Technical Risk
  Risks related to technology, tools, or systems.
Examples:
  New programming framework is unstable
  Integration failure between legacy system and new software
Project Management Risk
  Risks related to planning, scheduling, and control.
Examples:
  Poor effort estimation
  Inadequate communication among teams
  Unrealistic deadlines

## Slide 15: Types of Risks in IT Projects
Business / Organizational Risk
  Risks related to organizational environment.
Examples:
  Change in company strategy
  Budget cuts from management
  Client organization restructuring
External Risk
  Risks outside the organization’s control.
Examples:
  Changes in government IT regulations
  New data privacy laws (GDPR)
  Vendor failure

## Slide 16: Types of Risks in IT Projects
Resource Risk
  Risks related to human or material resources.
Examples:
  Skilled developers not available
  High employee attrition rate
  Dependency on a single expert
Security Risk
  Very critical in IT projects.
Examples:
  Data theft
  Malware attacks
  Unauthorized access

## Slide 17: Why Risk Needs to Be Managed
Risk management is essential because:
  Prevents project failure
  Reduces cost overruns
  Avoids schedule delays
  Improves decision-making
  Increases chances of project success
  Improves stakeholder confidence
  Helps identify opportunities
Example: Early identification of performance risk in a cloud application helps allocate better infrastructure, avoiding customer complaints later.

## Slide 18: Types of Risk Management (Risk Response Strategies)
Strategies for Negative Risks (Threats)
Risk Avoidance
  Eliminating the risk completely.
IT Example:
  Avoid using an untested technology
  Cancel a high-risk feature
Risk Mitigation
  Reducing the probability or impact of the risk.
IT Example:
  Conduct code reviews to reduce defect risk
  Provide training to reduce skill gap

## Slide 19: Types of Risk Management (Risk Response Strategies)
Risk Transfer
  Shifting the risk to a third party.
IT Example:
  Outsourcing security testing
  Purchasing cyber insurance
  Using SLA with cloud vendor
Risk Acceptance
  Accepting the risk and taking no immediate action.
IT Example:
  Accepting minor UI bugs and fixing them later
  Keeping contingency reserve

## Slide 20: Strategies for Positive Risks (Opportunities)
Exploit
Enhance
Share
Accept
Example: Using AI tools to speed up software testing.

## Slide 21: Risk Management Process

## Slide 22: Risk Management Process
Plan Risk Management
  Defines how to conduct risk management activities.
Outputs:
  Risk Management Plan
Example: Decide risk categories, probability scales, and reporting format.
Identify Risks
  Identifying all possible risks that may affect the project.
Tools:
  Brainstorming
  Checklists
  Expert judgment
  SWOT analysis
Example: Identify risk of API failure during system integration.
Output:
  Risk Register (initial)

## Slide 23: SWOT Analysis
SWOT stands for:
  S – Strengths
  W – Weaknesses
  O – Opportunities
  T – Threats
It is a strategic analysis technique used to evaluate internal and external factors that can affect a project or organization.
In PMBOK Project Risk Management, SWOT analysis is used during the Identify Risks process to identify:
  Negative risks (Threats) → things that may harm the project
  Positive risks (Opportunities) → things that may benefit the project
Classification:
  Strengths & Weaknesses → Internal factors
  Opportunities & Threats → External factors
Each SWOT factor is converted into specific, documented project risks and recorded in the Risk Register.

## Slide 24: SWOT Analysis
SWOT Element | Role in Risk Identification
Strengths | May reduce risks or create opportunities
Weaknesses | Internal sources of project threats
Opportunities | Positive risks to exploit or enhance
Threats | External sources of negative risks

## Slide 25: SWOT Analysis
Strengths (Internal – Positive)
  Experienced software development team
  Use of modern programming frameworks
  Strong management and stakeholder support
  Proven project management methodology
  Good development and testing infrastructure
Weaknesses (Internal – Negative)
  Limited cybersecurity expertise
  Incomplete or unclear user requirements
  Dependence on key technical resources
  Limited experience with third-party integrations
  Tight project schedule

## Slide 26: SWOT Analysis
Opportunities (External – Positive)
  Availability of cloud computing services
  Automated testing and DevOps tools
  Growing online market demand
  Reusable open-source components
  Vendor discounts for cloud services
Threats (External – Negative)
  Cybersecurity attacks and data breaches
  Frequent changes in technology
  Changes in data privacy regulations
  Third-party API or vendor failures
  Increased competition and market pressure

## Slide 27: Risk Management Process
Perform Qualitative Risk Analysis
  Prioritizing risks based on probability and impact.
Techniques:
  Probability–Impact Matrix
  Risk categorization
Example: High probability + high impact → Critical risk
Perform Quantitative Risk Analysis
  Numerical analysis of risk impact.
Techniques:
  Expected Monetary Value (EMV)
  Monte Carlo simulation
Example: Risk may cause ₹5,00,000 loss with 20% probability.

## Slide 28: Qualitative Risk Analysis (QRA)
Qualitative Risk Analysis is the process of prioritizing risks based on their probability of occurrence and impact on project objectives (scope, time, cost, quality, etc.) using subjective assessment techniques.
It is usually done first, because it’s faster and helps focus on high-priority risks for further quantitative analysis.
Steps in Qualitative Risk Analysis
Risk Identification
  Collect all risks from Risk Register (often using tools like SWOT, brainstorming, checklists).
Risk Probability Assessment
  Assess the likelihood of each risk occurring.
  Example scale: High / Medium / Low or 0–1 probability.
Risk Impact Assessment
  Assess the effect of each risk on project objectives.
  Example scale: High / Medium / Low or numerical score (1–5).
Risk Prioritization
  Combine probability and impact to calculate risk rating.
  Tools: Probability-Impact Matrix (P-I Matrix).
Risk Categorization (Optional)
  Group risks by source or type (technical, financial, external, organizational).
Update Risk Register
  Document risk score, priority, and notes for next steps.

## Slide 29: Qualitative Risk Analysis (QRA)
Types of Qualitative Risk Analysis Techniques
Probability-Impact Matrix
Risk Data Quality Assessment
Risk Urgency Assessment
Expert Judgment
Categorical (Risk Breakdown Structure) analysis

## Slide 30: Quantitative Risk Analysis (QuanRA)
Quantitative Risk Analysis is the numerical analysis of the effect of identified risks on project objectives, usually using statistical, mathematical, or simulation techniques.
It provides a numerical estimate of potential cost, time, or performance impact.
Steps in Quantitative Risk Analysis
Input Risk Data
  Use risks prioritized from Qualitative Risk Analysis.
Assign Numerical Values
  Probability: 0–1 or %
  Impact: monetary value, duration, or other measurable metric
Model Risk Effects
  Methods: Expected Monetary Value (EMV), Monte Carlo simulation, sensitivity analysis, decision tree analysis.
Analyze Risk Exposure
  Calculate Overall Project Risk Exposure = Σ (Probability × Impact)
Prioritize Risks Based on Numerical Impact
  Rank risks that have the highest quantitative effect.
Document Results in Risk Register
  Include numeric impact, probability, risk exposure, and recommended response.

## Slide 31: Quantitative Risk Analysis (QuanRA)

## Slide 32: Risk Management Process
6.5 Plan Risk Responses
Developing actions to address risks.
Example: Hiring backup developers to handle attrition risk.
6.6 Implement Risk Responses
Executing planned risk response actions.
6.7 Monitor Risks
Tracking identified risks and identifying new risks.
Example: Weekly risk review meetings.

## Slide 33: Risk Register
Records identified risks, their characteristics, and planned responses throughout the project lifecycle.
It is a living document updated continuously.
7.2 Components of a Risk Register
Risk ID
Risk Description
Risk Category
Probability
Impact
Risk Priority
Risk Owner
Response Strategy
Status

## Slide 34: Risk Register

## Slide 35: Project Evaluation - Performance Evaluation
Project evaluation measures how well the project is performing and whether objectives are met.
Uses Earned Value Management (EVM).
Key Metrics:
  Planned Value (PV)
  Earned Value (EV)
  Actual Cost (AC)
  Schedule Performance Index (SPI)
  Cost Performance Index (CPI)
Example:
  PV = ₹10,00,000
  EV = ₹8,00,000
  AC = ₹9,00,000
  CPI = EV / AC = 0.89 → Over budget
  SPI = EV / PV = 0.8 → Behind schedule
👉 Corrective actions required.

## Slide 36: Performance Evaluation

## Slide 37: Performance Evaluation

## Slide 38: Performance Evaluation

## Slide 39: Performance Evaluation – Burndown Chart
A Burn Down Chart is a graphical tool used in Agile project management to track:
Remaining work (tasks, story points, or hours)
Over time (usually days or sprints)
It helps monitor project progress and evaluate team performance against the plan.
Key Idea:
X-axis → Time (days, sprints)
Y-axis → Remaining work (effort units, story points, hours)
Line → Shows how work is “burning down” to zero

## Slide 40: Project Evaluation - Quality Evaluation
Checks whether deliverables meet quality standards.
Tools:
  Quality audits
  Control charts
  Inspections
Example: In a construction project:
  Concrete strength required: 30 MPa
  Test result: 27 MPa
  👉 Rework required to meet standards.

## Slide 41: Project Evaluation - Scope Evaluation
Ensures deliverables meet stakeholder requirements.
Example: Client requested:
Website with payment gateway
Mobile responsive design
If mobile responsiveness is missing: 👉 Deliverable is not accepted.

## Slide 42: Scope Evaluation
Scope Evaluation is the process of assessing whether the project’s deliverables meet the defined project scope and requirements.
Purpose:
Ensure deliverables match scope statement and WBS
Identify scope creep (unauthorized changes)
Confirm completion of milestones and deliverables
Support stakeholder approval and acceptance

## Slide 43: Scope Evaluation
2. Steps to Perform Scope Evaluation (PMBOK Approach)
Review Project Scope Statement & WBS
  Understand all approved deliverables, requirements, and exclusions.
Check Deliverables Against Requirements
  Verify if each deliverable meets quality and acceptance criteria.
Conduct Scope Verification
  Use formal reviews, inspections, walkthroughs, or audits with stakeholders.
Identify Scope Changes
  Detect unauthorized work, incomplete tasks, or missing requirements.
Document Findings
  Record discrepancies, deviations, and approved changes in scope documentation.
Obtain Formal Acceptance
  Stakeholders formally approve deliverables, ensuring closure of scope for the phase/project.
Update Project Records
  Update project management plan, scope baseline, and change log as needed.

## Slide 44: Scope Evaluation
3. Tools & Techniques for Scope Evaluation
Inspections / Reviews / Audits
Checklists based on scope baseline
Variance analysis (planned vs actual deliverables)
Performance measurement (e.g., Earned Value metrics)
Expert judgment

## Slide 45: Project Evaluation - Schedule Evaluation
Evaluates project progress against the schedule baseline.
Tools:
Gantt charts
Milestone reviews
Critical Path Method (CPM)
Example: If testing was planned for 2 weeks but takes 4 weeks: 👉 Schedule variance identified and corrective planning done.

## Slide 46: Post-Project Evaluation
Benefits Realization Analysis
Checks whether expected benefits are achieved.
Example: ERP project expected:
20% reduction in operating cost
After 1 year:
Actual reduction: 15%
👉 Partial success; improvement opportunities identified.

## Slide 47: Post-Project Evaluation
Lessons Learned Evaluation
Identifies:
What went well
What went wrong
What can be improved
Example: Lesson learned:
Early stakeholder involvement reduced change requests
👉 Documented for future projects.

## Slide 48: Post-Project Evaluation
3.3 Customer Satisfaction Evaluation
Measures stakeholder satisfaction.
Tools:
Surveys
Feedback forms
Interviews
Example: Client rates project:
Quality: 4/5
Schedule: 3/5
Communication: 5/5

## Slide 49: Project Analysis and Evaluation Framework
Project analysis is commonly divided into three major assessments:
Strategic Assessment
Technical Assessment
Economic (Financial) Assessment
3. Strategic Assessment
3.1 Meaning
Strategic assessment evaluates how well a project supports the organization’s vision, mission, and long-term strategy.
PMBOK emphasizes that projects should deliver business value, not just outputs.

## Slide 50: Project Analysis and Evaluation Framework
3.2 Key Strategic Questions
Does the project align with organizational goals?
Does it provide competitive advantage?
Is it aligned with regulatory, social, or environmental requirements?
Does it support growth, innovation, or sustainability?
3.3 Strategic Assessment Tools
SWOT Analysis
PESTLE Analysis
Porter’s Five Forces
Balanced Scorecard
Strategic Alignment Matrix

## Slide 51: Project Analysis and Evaluation Framework
3.4 Example
Organization Goal: Expand digital services
Project A: Develop a mobile banking application Project B: Renovate office buildings
Strategic Evaluation:
Project A supports digital transformation and customer reach
Project B improves infrastructure but does not directly support strategy
Conclusion: Project A scores higher strategically.

## Slide 52: Technical Assessment
Technical assessment evaluates whether the project is technically feasible using available technology, skills, infrastructure, and time.
4.2 Key Technical Factors
Availability of technology
Technical complexity
Resource skills and expertise
Integration with existing systems
Technical risks
Compliance with standards

## Slide 53: Technical Assessment
4.3 Technical Assessment Questions
Can the project be implemented with current technology?
Are skilled resources available?
Is the technology proven or experimental?
What are the technical risks?
4.4 Example
Project: Implement an AI-based customer support system
Required AI expertise is limited
Existing IT systems require integration
Technology is emerging but proven
Assessment Result: Technically feasible with moderate risk and training requirements.

## Slide 54: Economic (Financial) Assessment
Economic assessment evaluates whether the financial benefits outweigh the costs over the project life cycle.
This is a key component of the Business Case in PMBOK.
5.2 Components of Economic Assessment
Initial investment cost
Operating and maintenance costs
Tangible and intangible benefits
Project life span
Time value of money
Risk and uncertainty

## Slide 55: Economic (Financial) Assessment
6. Cost–Benefit Evaluation Techniques
These techniques are used to compare and select projects based on financial performance.

## Slide 56: Comparison of projects based on cost benefit evaluation
Cost-Benefit Analysis (CBA) is a financial evaluation technique used to compare different projects or alternatives based on:
Costs → Investment, development, operating, maintenance
Benefits → Revenue, cost savings, productivity gains
Net Profit / Net Benefit is calculated as:
Purpose:
Determine financial feasibility of a project
Help prioritize projects when multiple options exist
Support management decision-making

## Slide 57: Cost-Benefit Evaluation Technique
2. Steps to Compare Projects Using Net Profit
List Alternatives / Projects
  Identify all IT projects under consideration.
Estimate Costs for Each Project
  Include development cost, hardware, software licenses, training, maintenance.
Estimate Benefits for Each Project
  Revenue, cost savings, efficiency improvements, productivity gains.
Calculate Net Profit (Net Benefit)
  Net Profit = Benefits − Costs
Rank Projects
  Higher net profit → higher priority for implementation.
Consider Non-Financial Factors (Optional)
  Strategic alignment, risk, regulatory compliance, customer satisfaction.

## Slide 58: Example

## Slide 59: Example
Step 4: Comparison & Decision
Project A → Higher net profit ($80,000) → preferred choice
Project B → Lower net profit ($55,000) → second priority
Interpretation: Even though Project B costs less, Project A provides higher financial benefit and is therefore prioritized.

## Slide 60: Payback Period
The payback period is the time it takes for a project to recover its initial investment from its net benefits or cash inflows.
Payback Period (Years)=Annual Net BenefitsInitial Investment​
Purpose:
Evaluate the financial feasibility of a project
Compare projects with different costs and benefits
Helps management choose faster-returning investments
Key Concept:
Shorter payback period → faster recovery → lower risk
Longer payback period → delayed return → higher risk

## Slide 61: Payback Period
2. Steps to Compare Projects Using Payback Period
List the projects / alternatives
Estimate the initial investment (costs)
Estimate annual benefits or savings
Calculate payback period for each project
  If benefits vary yearly, cumulative cash flow is used
Rank the projects
  Lower payback period → preferred choice
Consider other factors
  Strategic alignment, risk, non-financial benefits

## Slide 62: Example

## Slide 63: Return on Investment
ROI is a financial metric that measures the profitability of an investment by comparing the net benefits (or profit) to the initial investment.
The formula for calculating ROI is:
Where:
Net Profit = Total Benefits - Total Costs
Initial Investment is the upfront cost of the project.
Purpose:
Measure how effectively a project generates profit relative to its costs.
Help decision-makers compare multiple projects to determine which one offers the best return for the money invested.
ROI Interpretation:
A higher ROI means higher profitability relative to cost.
A negative or low ROI suggests that the investment may not be worthwhile.

## Slide 64: Return on Investment
2. Steps to Compare Projects Using ROI
Identify and list the projects to be compared.
Estimate the total costs for each project (initial investment + operational costs).
Estimate the total benefits or returns generated from the project over a given time period (e.g., yearly, 5 years).
Calculate Net Profit for each project:
Calculate ROI for each project using the formula:
Rank the projects based on their ROI—higher ROI is typically preferred.
Consider other non-financial factors, such as risk, strategic alignment, and operational impact.

## Slide 65: Example

## Slide 66: Example

## Slide 67: Net Present Value
Net Present Value (NPV) is a financial metric that calculates the difference between the present value of cash inflows (benefits) and the present value of cash outflows (costs) over a specific time period. It accounts for the time value of money (i.e., money today is worth more than money in the future).
The formula for NPV is:
Where:
= Cash inflow at time
= Discount rate (cost of capital, risk-adjusted rate)
= Time period
= Initial investment (cash outflow at time 0)
Purpose:
NPV helps determine whether the project adds value to the company and whether it’s a financially viable investment.
A positive NPV indicates that the project is expected to generate more value than its cost, making it a good investment.
A negative NPV suggests the project will destroy value and should be avoided.

## Slide 68: Net Present Value
Steps to Compare Projects Using NPV
Identify the projects to be compared.
Estimate the initial investment for each project.
Forecast the expected cash inflows (benefits) for each period (e.g., annually).
Choose the discount rate (r) based on the company’s cost of capital or risk-adjusted rate.
Calculate the present value of each cash inflow using the formula.
Subtract the initial investment to calculate the NPV.
Compare NPVs: Higher NPV is typically preferred.
Consider other non-financial factors: such as strategic alignment, risks, or customer impact.

## Slide 69: Example

## Slide 70: Example

## Slide 71: Example

## Slide 72: Example

## Slide 73: Internal Rate of Return
The Internal Rate of Return (IRR) is the discount rate at which the Net Present Value (NPV) of a project becomes zero. In other words, it is the rate at which the present value of cash inflows equals the initial investment.
Mathematically, IRR is the rate that satisfies the following equation:
Where:
= Cash inflows at time
= Internal Rate of Return (IRR)
= Initial investment (cash outflow at time 0)
= Time period
Purpose:
IRR is used to determine the expected rate of return for a project.
It is a key metric in deciding whether to proceed with an investment.
IRR helps compare multiple projects—projects with higher IRR are usually preferred.

## Slide 74: Internal Rate of Return
2. Steps to Compare Projects Using IRR
Identify the projects to be compared.
Estimate the initial investment for each project.
Forecast the expected cash inflows (benefits) for each year or period.
Use an iterative process (trial and error or financial calculator) to find the IRR where the NPV = 0.
Compare IRRs of different projects.
  If the IRR is higher than the required rate of return (hurdle rate) or cost of capital, the project is considered financially viable.
Consider other factors, such as risk, strategic alignment, and time horizons.

## Slide 75: Example

## Slide 76: Example