## Slide 1: Risk
A project risk is an uncertain event or condition that, if it occurs, has a positive or negative effect on one or more project objectives such as:
  Scope
  Schedule
  Cost
  Quality
📌 Risk ≠ Problem
Risk: May happen
Issue/Problem: Has already happened

## Slide 2: Risk Management
Risk is an uncertain event or condition that, if it occurs, has a positive or negative effect on one or more project objectives such as scope, schedule, cost, quality, or performance.
Key points:
  Risk is about uncertainty
  It may have negative effects (threats) or positive effects (opportunities)
  Risks exist in all projects, especially IT projects
Characteristics of Risk
  Future-oriented
  Uncertain in nature
  Has a cause and an effect
  Can impact cost, time, quality, scope, or reputation
  Can be managed but not completely eliminated

## Slide 4: Risk Managment
Types of Risk
Based on Impact
Negative Risk (Threat)
  Events that can harm the project.
  Example (IT Company):
  Cybersecurity breach delaying software release
  Key developer resigns during critical phase
Positive Risk (Opportunity)
  Events that can benefit the project.
  Example:
  Use of a new automation tool reduces development time
  Client requests additional features with extra payment

## Slide 5: Types of Risk in IT Projects
Technical Risk
  Risks related to technology, tools, or systems.
Examples:
  New programming framework is unstable
  Integration failure between legacy system and new software
Project Management Risk
  Risks related to planning, scheduling, and control.
Examples:
  Poor effort estimation
  Inadequate communication among teams
  Unrealistic deadlines

## Slide 6: Types of Risks in IT Projects
Business / Organizational Risk
  Risks related to organizational environment.
Examples:
  Change in company strategy
  Budget cuts from management
  Client organization restructuring
External Risk
  Risks outside the organization’s control.
Examples:
  Changes in government IT regulations
  New data privacy laws (GDPR)
  Vendor failure

## Slide 7: Types of Risks in IT Projects
Resource Risk
  Risks related to human or material resources.
Examples:
  Skilled developers not available
  High employee attrition rate
  Dependency on a single expert
Security Risk
  Very critical in IT projects.
Examples:
  Data theft
  Malware attacks
  Unauthorized access

## Slide 8: Why Risk Needs to Be Managed
Risk management is essential because:
  Prevents project failure
  Reduces cost overruns
  Avoids schedule delays
  Improves decision-making
  Increases chances of project success
  Improves stakeholder confidence
  Helps identify opportunities
Example: Early identification of performance risk in a cloud application helps allocate better infrastructure, avoiding customer complaints later.

## Slide 9: Importance of Risk Management
Risk Management helps to:
  Reduce project failures
  Improve decision-making
  Increase probability of project success
  Protect project objectives
  Identify opportunities (positive risks)
Example
If a software project ignores the risk of changing requirements, it may lead to:
  Cost overrun
  Schedule delay
  Poor quality

## Slide 10: PMBOK Risk Management Processes
According to PMBOK, Project Risk Management consists of 7 processes:
  Plan Risk Management
  Identify Risks
  Perform Qualitative Risk Analysis
  Perform Quantitative Risk Analysis
  Plan Risk Responses
  Implement Risk Responses
  Monitor Risks

## Slide 11: Plan Risk Management
The process of defining how to conduct risk management activities for the project.
Outputs
  Risk Management Plan
Contents of Risk Management Plan
  Risk methodology
  Roles and responsibilities
  Risk categories
  Probability and impact definitions
  Risk thresholds
  Reporting formats
Example
A construction project decides:
  High risk = delay > 30 days
  Risk review every 2 weeks

## Slide 12: Identify Risks
The process of identifying individual project risks and documenting their characteristics.
Techniques
  Brainstorming
  Expert judgment
  Checklists
  SWOT analysis
  Document review
  Interviews
Output
  Risk Register
Risk Register Contains
  Risk description
  Risk cause
  Risk impact
  Risk owner
Example
Risk:
  “Key developer may leave the project.”
Cause: Better job offer Impact: Schedule delay

## Slide 13: Perform Qualitative Risk Analysis
The process of prioritizing risks based on:
  Probability of occurrence
  Impact on project objectives
Tools
  Probability–Impact Matrix
  Risk categorization
  Expert judgment
Risk Rating Formula
  Risk Score = Probability × Impact

## Slide 14: Objectives of Qualitative Risk Analysis
Rank risks based on importance
Identify critical risks requiring immediate response
Reduce the number of risks for quantitative analysis
Support better decision-making
Optimize use of time and resources

## Slide 15: Steps to perform qualitative risk analysis
Step 1: Review Identified Risks
Use the Risk Register
Ensure risk statements are clear and complete
📌 Example: Risk: “Delay in delivery of hardware due to supplier issues.”

## Slide 16: Steps to perform qualitative risk analysis

## Slide 17: Steps to perform qualitative risk analysis
Step 5: Risk Prioritization
Assign risk ratings (High / Medium / Low)
Sort risks based on priority
Focus on top-ranked risks
📌 Example: Critical risks → Immediate response Low risks → Watch list
Step 6: Assign Risk Owners
Each risk is assigned to a responsible person
Ensures accountability
📌 Example: Vendor delay risk → Procurement Manager

## Slide 18: Steps to perform qualitative risk analysis
Step 7: Update Risk Register
The risk register is updated with:
Probability
Impact
Risk rating
Risk owner
Response strategy (optional)

## Slide 19: Types of Qualitative Risk Analysis
1. Probability-Based Analysis
Focuses only on likelihood
Used in early project stages
📌 Example: Risk of requirement change is high
2. Impact-Based Analysis
Focuses on severity of consequences
📌 Example: Data loss has very high impact
3. Probability–Impact Analysis
Most common method
Combines probability and impact
📌 Example: High probability + Medium impact = High risk

## Slide 20: Types of Qualitative Risk Analysis
4. Risk Urgency Assessment
Evaluates how soon the risk may occur
📌 Example: Risk happening next week → High urgency

## Slide 21: Tools used
Expert judgment
Brainstorming
Probability–Impact Matrix
Risk categorization
SWOT analysis
Risk data quality assessment

## Slide 22: Expert Judgment
Expert judgment involves using the knowledge and experience of subject matter experts (SMEs), such as:
Senior project managers
Technical experts
Industry specialists
Consultants
Experts help in:
Identifying risks
Assessing probability and impact
Prioritizing risks
Suggesting response strategies
Example
In a software development project, an experienced architect states:
“Using a new framework has a high risk of integration failure.”
Based on this expert input:
Probability → High
Impact → High
Risk Priority → Critical
📌 Expert judgment is especially useful when historical data is limited.

## Slide 23: Brainstorming
Brainstorming is a group creativity technique where project team members and stakeholders:
Freely suggest potential risks
Avoid criticism during idea generation
Aim to identify as many risks as possible
It encourages open discussion and collective thinking.
Example
In a construction project, a brainstorming session identifies risks such as:
Labor strike
Delay in material delivery
Bad weather
Equipment breakdown
These risks are then documented in the risk register.
📌 Brainstorming is commonly used during the risk identification phase, but also supports qualitative analysis.

## Slide 24: Probability–Impact Matrix
A Probability–Impact (P–I) Matrix is a visual tool used to:
Combine probability and impact
Rank risks as High, Medium, or Low
Identify which risks need immediate action
Risk Score = Probability × Impact

## Slide 25: Risk Categorization
Risk categorization involves grouping risks based on their source or nature, making it easier to:
Identify common problem areas
Assign responsibility
Plan category-specific responses
Often organized using a Risk Breakdown Structure (RBS).
Common Risk Categories
Technical
Schedule
Cost
Resource
External
Organizational

## Slide 26: SWOT Analysis
SWOT Analysis evaluates:
Strengths
Weaknesses
Opportunities
Threats
It helps identify both positive and negative risks.

## Slide 27: Example

## Slide 28: Pros Cons
8. Advantages of Qualitative Risk Analysis
Simple and fast
Easy to understand
Useful when data is limited
Helps focus on major risks
9. Limitations of Qualitative Risk Analysis
Subjective
Depends on expert judgment
Not suitable for cost estimation
Less accurate for complex projects

## Slide 29: Perform quantitative Risk Analysis
Quantitative Risk Analysis is the process of numerically analyzing the effect of identified risks on project objectives, such as:
Schedule
Cost
Scope
Quality
Unlike qualitative risk analysis, which focuses on ranking risks as High, Medium, or Low, quantitative analysis uses mathematical models and data to estimate the magnitude and probability of the impact.
The aim is to provide a numeric estimate of the potential impact of risks, helping project managers make informed decisions regarding risk responses.
When to Use QRA?
Large, complex projects
When decision-makers require precise information on risk impact
When accurate cost and schedule predictions are crucial

## Slide 30: Steps in Quantitative Risk Analysis
Step 1: Define the Risk Parameters
Before any quantitative analysis can begin, the following must be clearly defined:
Risk events
Impacts
Risk responses
Example
Risk: Delay in hardware delivery
Probability: 30%
Impact: 2 weeks of delay

## Slide 31: Steps in Quantitative Risk Analysis
Step 2: Gather Data and Information
This involves collecting data to understand the probabilities and impacts of risks. Data sources may include:
Historical data
Expert judgment
Monte Carlo simulations
Example
Historical data suggests that hardware delays have occurred 25% of the time, with an average impact of 2 weeks.

## Slide 32: Steps in Quantitative Risk Analysis
Step 3: Perform Quantitative Risk Modeling
Use mathematical models to calculate the expected value of each risk. Common models include:
Expected Monetary Value (EMV)
Monte Carlo Simulation
Decision Tree Analysis
Step 4: Analyze and Interpret Results
Once the modeling is complete, interpret the results:
Risk exposure: the total value of risk
Range of possible outcomes: high vs low-risk impact
Most likely scenario: based on probability distributions
Step 5: Update Risk Register
After the analysis, update the Risk Register to:
Reflect numerical risk values
Include appropriate risk responses

## Slide 33: Types of Quantitative Risk Analysis
1. Expected Monetary Value (EMV)
EMV is used to calculate the average outcome of a risk event by multiplying its probability by its potential impact.
Formula:
EMV = Probability × Impact
Example
Risk: Vendor delay
Probability: 20% (0.2)
Impact: $50,000
EMV = 0.2 × 50,000 = $10,000
Interpretation: The expected cost of the vendor delay is $10,000.

## Slide 34: Types of Quantitative Risk Analysis
2. Monte Carlo Simulation
Monte Carlo Simulation is a probabilistic model that uses random sampling to simulate a wide range of possible outcomes, based on the probability distributions of input variables. This results in a range of possible outcomes with associated probabilities.
How it works:
Define the input variables (risks).
Define their probability distributions.
Run multiple simulations to generate a range of outcomes.
Example
For a construction project, the project manager might simulate the completion time with uncertainties in resource availability, weather, and labor efficiency. After running 10,000 simulations, they find the probability distribution of completion times.
📌 Result: There is a 70% chance the project will finish in 12–14 months and a 30% chance it will take 15–18 months.

## Slide 35: Types of Quantitative Risk Analysis
Decision Tree Analysis is a graphical tool used to evaluate decisions under uncertainty. It helps in:
Evaluating different decision paths
Analyzing risks based on different choices
Steps:
Draw decision tree nodes: Decision points and possible outcomes.
Calculate expected values for each branch.
Example:
A project faces the decision of using a new supplier.
Option A (new supplier): 80% chance of timely delivery (impact: $100,000), 20% chance of delay (impact: $200,000).
Option B (current supplier): Guaranteed timely delivery (impact: $0).
The decision tree for Option A is:

## Slide 36: Types of Quantitative Risk Analysis

## Slide 37: Key Advantages of Quantitative Risk Analysis
6. Key Advantages of Quantitative Risk Analysis
Provides numerical estimates of risk impact
Helps prioritize risks based on financial and schedule outcomes
Facilitates better decision-making by providing clear projections
Supports cost-benefit analysis and optimal risk responses

## Slide 38: Limitations of Quantitative Risk Analysis
7. Limitations of Quantitative Risk Analysis
Requires good data: Accurate risk models depend on reliable historical data.
Time-consuming: Requires significant effort to gather data and perform modeling.
Complexity: Advanced models (e.g., Monte Carlo) require specialized tools and knowledge.

## Slide 39: Comparison
. Overview
Qualitative Risk Analysis
Definition: The process of assessing the impact and probability of risks using non-numeric methods, often through expert judgment, brainstorming, and prioritization.
Focus: Relative ranking of risks (High, Medium, Low) based on their likelihood and impact.
Output: Risk Register with risk ratings (e.g., high, medium, low).
When Used: Early in the project when data is limited or time is constrained, or when precise data is unavailable.
Quantitative Risk Analysis
Definition: The process of assessing risks using numeric models and statistical methods to determine the magnitude and probability of their impact on project objectives.
Focus: Numerical analysis of risk impact on schedule, cost, and other project objectives.
Output: Quantified risk values (e.g., expected monetary value, Monte Carlo simulations).
When Used: For large, complex, or high-stakes projects where precise data and detailed analysis are crucial.

## Slide 40: Difference

## Slide 41: Example Comparison
Scenario: Software Development Project
Risk: Delay in delivery of key software components
Qualitative Risk Analysis Example
Probability: 40% chance of delay
Impact: Delay in project delivery by 2 weeks, costing $20,000
After applying Probability-Impact Matrix, this risk is assessed as High.
Risk Rating: High Priority (Needs immediate attention)
Output:
Risk Register would note: Risk: Delay in key component delivery Probability: 40% Impact: 2 weeks delay, $20,000 cost Priority: High

## Slide 42: Example Comparison
Quantitative Risk Analysis Example
Expected Monetary Value (EMV):
  Probability: 40% (0.4)
  Impact (Cost): $20,000
EMV = Probability × Impact = 0.4 × 20,000 = $8,000
Monte Carlo Simulation:
  The project manager runs a Monte Carlo simulation to model the effect of potential delays from multiple risks (e.g., key components, resource issues, testing delays) on the project's total cost.
After running 10,000 simulations, the model predicts a 90% probability that the project will exceed the budget by $15,000.
Output:
The EMV for this risk (delay) is $8,000.
Monte Carlo simulation predicts $15,000 additional cost due to risks.

## Slide 43: Perform Quantitative Risk Analysis
The process of numerically analyzing the effect of identified risks on project objectives.
Used When
  Large, complex, high-risk projects
  Budget and schedule accuracy is critical
Techniques
  Monte Carlo Simulation
  Decision Tree Analysis
  Expected Monetary Value (EMV)
  Sensitivity Analysis
EMV Example
  Risk: Server crash
  Probability = 20%
  Cost impact = ₹1,00,000
  EMV = 0.2 × 1,00,000 = ₹20,000

## Slide 44: Plan Risk Responses
The process of developing options and actions to address risks.
Strategies for Negative Risks (Threats)
Avoid
  Eliminate the risk
  Example: Use proven technology instead of new one
Mitigate
  Reduce probability or impact
  Example: Add extra testing to reduce defects
Transfer
  Shift risk to third party
  Example: Insurance, outsourcing
Accept
  Take no action
  Example: Small delay risk accepted

## Slide 45: Plan Risk Responses
Strategies for Positive Risks (Opportunities)
Exploit
  Ensure opportunity happens
  Example: Assign best resources to finish early
Enhance
  Increase probability or benefit
  Example: Add skilled staff to improve performance
Share
  Partner with others
  Example: Joint venture
Accept
  Take advantage if it occurs

## Slide 46: Implement Risk Responses
The process of executing the planned risk response actions.
Key Points
  Risk owners implement responses
  Actions are added to project schedule
  Requires coordination and tracking
Example
Risk: Data loss Response: Daily automated backups Implementation: Backup system installed

## Slide 47: Monitor Risks
The process of tracking identified risks, monitoring residual risks, and identifying new risks.
Activities
  Risk audits
  Risk reviews
  Status meetings
  Update risk register
  Check effectiveness of responses
Example
  A previously low-risk vendor delay becomes high-risk due to supply chain issues.

## Slide 48: Risk Categories (RBS – Risk Breakdown Structure)
Common categories:
  Technical risks
  Schedule risks
  Cost risks
  Resource risks
  External risks
  Organizational risks

## Slide 49: Key Benefits of Risk Management
Reduced uncertainty
Better planning
Higher success rate
Improved stakeholder confidence
Better cost and schedule control

## Slide 50: PERT and Risk Management
PERT (Program Evaluation and Review Technique) is a project management tool that helps evaluate the uncertainty in project timelines, particularly when estimating task durations. It is particularly useful in risk management because it accounts for uncertainty by considering multiple possible outcomes for the duration of project activities.
In the PMBOK (Project Management Body of Knowledge), risk management is emphasized as a key process to ensure the project stays within scope, time, and cost constraints. PERT can be an effective tool for managing project time uncertainty and assessing the impacts of risks on the schedule.
PERT Overview
In PERT, you estimate the duration of a task by considering three possible values:
Optimistic (O): The best-case scenario (the shortest time to complete the task, assuming everything goes perfectly).
Pessimistic (P): The worst-case scenario (the longest time to complete the task, assuming all risks and issues occur).
Most Likely (M): The most realistic scenario based on the current conditions.
These values are used to calculate an expected duration for the task, often referred to as the Expected Time (TE), using the following formula:
This formula gives more weight to the Most Likely duration, but also incorporates the potential variability of the task's duration, allowing project managers to account for uncertainty.

## Slide 51: Step-by-Step: Using PERT to Manage Uncertainty in a Project
Identify Risk Events and Tasks:
  Break down the project into individual tasks and identify areas where uncertainty may exist (e.g., technical challenges, resource availability, or external factors like weather).
  For example, if you’re developing software, certain tasks may involve uncertainty around third-party integrations or data migrations.
Estimate Task Durations Using PERT: For each identified task, gather input from your team or subject matter experts to estimate the three values:
  Optimistic (O): If everything goes as planned (e.g., no issues with integration, everything works smoothly).
  Pessimistic (P): If the worst happens (e.g., significant delays in integration, technical difficulties).
  Most Likely (M): The most probable duration based on available information.
For instance:
  Task: Develop Login Feature
    Optimistic (O) = 3 days
    Most Likely (M) = 5 days
    Pessimistic (P) = 8 days
Using the PERT formula, you calculate the Expected Duration (TE):

## Slide 52: Step-by-Step: Using PERT to Manage Uncertainty in a Project
Construct the PERT Network:
  Create a PERT chart (a flowchart of tasks, their dependencies, and estimated durations).
  The chart allows you to visualize the sequence of tasks, identify critical paths, and understand where uncertainty might affect the overall project schedule.
Assess the Project Schedule Risk:
  Calculate the Expected Project Duration by applying PERT estimates across all tasks.
  Critical Path Method (CPM) can be combined with PERT to identify the critical path, which is the longest path in the project. Delays in tasks on the critical path will directly impact the project’s completion date.
  Risk Identification: If a task has high uncertainty (e.g., a large difference between optimistic and pessimistic estimates), it should be flagged for potential risks.
Risk Analysis (Quantitative):
  You can simulate the effects of different risks on the schedule using Monte Carlo simulations to model different scenarios based on the PERT estimates.
  By generating multiple possible scenarios with varying task durations, you can estimate the likelihood of completing the project within a given timeframe, considering all uncertainties.
Monitor and Adjust:
  During project execution, continually track task progress. If tasks are slipping into the pessimistic range (P), reevaluate and adjust the project schedule, resources, or scope to mitigate risk.
  You can also update your PERT estimates if new risks emerge or if the project's scope changes.

## Slide 53: Step-by-Step: Using PERT to Manage Uncertainty in a Project
Example: Managing Uncertainty in an IT Project Using PERT
Let’s consider an IT project: building a new customer relationship management (CRM) system for a client.
Task: Database Migration
  Optimistic (O) = 4 days (Assume no technical issues with migration and data integrity).
  Most Likely (M) = 6 days (Normal migration with typical challenges, but no major roadblocks).
  Pessimistic (P) = 10 days (Assume significant issues with data quality, integration errors, and additional debugging).
Step 1: Calculate Expected Duration (TE) for Database Migration
Step 2: Estimate Project Duration
Let's say the project has 5 main tasks, and you’ve calculated the expected duration for each using PERT. The tasks are:
  Design Database Schema: 4 days (most likely)
  Database Migration: 6.33 days (expected duration from above)
  API Integration: 5 days
  User Interface Development: 7 days
  Testing: 4 days

## Slide 54: Step-by-Step: Using PERT to Manage Uncertainty in a Project
You can now construct a PERT network diagram to represent the tasks and their dependencies.
Step 3: Identify the Critical Path
Using the Critical Path Method (CPM), you can calculate the longest path and identify which tasks are critical to finishing the project on time.
Let’s assume the critical path involves Database Migration, API Integration, and Testing.
The total expected duration is the sum of the durations of tasks on the critical path:
Step 4: Risk Analysis and Mitigation
  If the Database Migration task were to take longer than expected (e.g., the pessimistic estimate of 10 days), this would push the overall project timeline significantly, especially if it’s on the critical path.
  Risk mitigation: You can buffer this task by allocating extra resources or planning for alternative strategies (like using a more efficient migration tool).
Conclusion: Using PERT in Risk Management
  By using PERT to model uncertainty, you can assess how variations in task durations due to risks will affect the overall project. In risk management, this is important because it allows you to:
  Quantify uncertainty: By estimating the range of possible outcomes for each task, you can assess the likelihood of completing the project on time.
  Prioritize risks: Tasks with large variability (a significant difference between O, M, and P) may require closer monitoring or more proactive risk management strategies.
  Make data-driven decisions: With the PERT formula and potentially Monte Carlo simulations, you can predict more realistic project timelines and prepare contingency plans for delays.